## Primavera Activities
DESIGN1 — PRIMAVERA P6 ACTIVITY DATA
Activity ID | Activity Name | WBS Code | WBS | Status | Progress % | Start | Finish | Duration (days) | Predecessors | Total Float (h) | Early Start | Early Finish | Late Start | Late Finish
A1000 | Project Initiation | DESIGN1.1 | Tinker Line > MilesStones | Completed | 0 | 2026-09-27 08:00 | 2026-09-27 08:00 | 0 |  | 8 | 2026-09-27 08:00 | 2026-09-27 08:00 | 2026-09-28 08:00 | 2026-09-28 08:00
A1010 | Requirements & Planning | DESIGN1.1 | Tinker Line > MilesStones | Completed | 0 | 2026-09-29 16:00 | 2026-09-29 16:00 | 0 | A1760 (FS) | 544 | 2026-09-29 16:00 | 2026-09-29 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1030 | Mechanical Design | DESIGN1.1 | Tinker Line > MilesStones | In Progress | 0 | 2026-10-30 16:00 | 2026-10-30 16:00 | 0 | A1830 (FS) | 328 | 2026-10-30 16:00 | 2026-10-30 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1040 | Electrical & Control System | DESIGN1.1 | Tinker Line > MilesStones | On Hold | 0 | 2026-12-02 16:00 | 2026-12-02 16:00 | 0 | A1850 (FS) | 184 | 2026-12-02 16:00 | 2026-12-02 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1050 | Procurement | DESIGN1.1 | Tinker Line > MilesStones | Not Started | 0 | 2026-12-08 16:00 | 2026-12-08 16:00 | 0 | A1420 (FS) | 144 | 2026-12-08 16:00 | 2026-12-08 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1060 | Manufacturing | DESIGN1.1 | Tinker Line > MilesStones | Not Started | 0 | 2026-10-30 16:00 | 2026-10-30 16:00 | 0 | A1830 (FS) | 328 | 2026-10-30 16:00 | 2026-10-30 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1070 | Assembly & Integration | DESIGN1.1 | Tinker Line > MilesStones | Not Started | 0 | 2026-12-17 16:00 | 2026-12-17 16:00 | 0 | A1440 (FS) | 80 | 2026-12-17 16:00 | 2026-12-17 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1090 | Testing & Commissioning | DESIGN1.1 | Tinker Line > MilesStones | Not Started | 0 | 2026-12-25 16:00 | 2026-12-25 16:00 | 0 | A1620 (FS), A1840 (FS) | 24 | 2026-12-25 16:00 | 2026-12-25 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1100 | Handover | DESIGN1.1 | Tinker Line > MilesStones | Not Started | 0 | 2026-12-28 16:00 | 2026-12-28 16:00 | 0 | A1630 (FS) | 8 | 2026-12-28 16:00 | 2026-12-28 16:00 | 2026-12-29 16:00 | 2026-12-29 16:00
A1110 | Define Project Objectives | DESIGN1.2 | Tinker Line > Project Initiation | Completed | 0 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2 | A1000 (SS) | 8 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2026-09-28 08:00 | 2026-09-29 16:00
A1120 | Sketches | DESIGN1.2 | Tinker Line > Project Initiation | Completed | 0 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2 | A1110 (SS) | 8 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2026-09-28 08:00 | 2026-09-29 16:00
A1130 | Settle to Idea | DESIGN1.2 | Tinker Line > Project Initiation | Completed | 0 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2 | A1120 (SS), A1120 (FF) | 8 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2026-09-28 08:00 | 2026-09-29 16:00
A1140 | Set Initial Project Schedule | DESIGN1.3 | Tinker Line > Requirements & Planning | Completed | 0 | 2026-09-28 08:00 | 2026-09-28 16:00 | 1 | A1130 (SS +8h) | 8 | 2026-09-28 08:00 | 2026-09-28 16:00 | 2026-09-29 08:00 | 2026-09-29 16:00
A1150 | Estimate BOM | DESIGN1.3 | Tinker Line > Requirements & Planning | Completed | 0 | 2026-09-28 08:00 | 2026-09-28 16:00 | 1 | A1140 (SS) | 16 | 2026-09-28 08:00 | 2026-09-28 16:00 | 2026-09-30 08:00 | 2026-09-30 16:00
A1760 | Assign Resources | DESIGN1.3 | Tinker Line > Requirements & Planning | Completed | 0 | 2026-09-29 08:00 | 2026-09-29 16:00 | 1 | A1140 (SS +8h), A1150 (SS) | 8 | 2026-09-29 08:00 | 2026-09-29 16:00 | 2026-09-30 08:00 | 2026-09-30 16:00
A1160 | LID | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-09-30 08:00 | 2026-09-30 16:00 | 1 | A1760 (FS) | 152 | 2026-09-30 08:00 | 2026-09-30 16:00 | 2026-10-22 08:00 | 2026-10-22 16:00
A1170 | Base | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-06 08:00 | 2026-10-06 16:00 | 1 | A1760 (FS +40h) | 112 | 2026-10-06 08:00 | 2026-10-06 16:00 | 2026-10-22 08:00 | 2026-10-22 16:00
A1180 | Electrical Box | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-06 08:00 | 2026-10-06 16:00 | 1 | A1760 (FS +40h) | 24 | 2026-10-06 08:00 | 2026-10-06 16:00 | 2026-10-09 08:00 | 2026-10-09 16:00
A1190 | Magnetic End Effector | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | In Progress | 0 | 2026-10-07 08:00 | 2026-10-08 16:00 | 2 | A1760 (FS +40h), A1160 (FS), A1170 (FS) | 480 | 2026-10-07 08:00 | 2026-10-08 16:00 | 2026-12-28 08:00 | 2026-12-29 16:00
A1200 | Design Magazine Parts | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-06 08:00 | 2026-10-07 16:00 | 2 | A1760 (FS +40h) | 8 | 2026-10-06 08:00 | 2026-10-07 16:00 | 2026-10-07 08:00 | 2026-10-08 16:00
A1210 | Shaft Analysis | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-11 08:00 | 2026-10-11 16:00 | 1 | A1680 (FS +8h) | 464 | 2026-10-11 08:00 | 2026-10-11 16:00 | 2026-12-29 08:00 | 2026-12-29 16:00
A1340 | Actuator Sizing | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-16 08:00 | 2026-10-18 16:00 | 2 | A1680 (FS +8h), A1670 (FS +8h) | 416 | 2026-10-16 08:00 | 2026-10-18 16:00 | 2026-12-28 08:00 | 2026-12-29 16:00
A1590 | Storage | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-06 08:00 | 2026-10-11 16:00 | 5 | A1760 (FS +40h) | 464 | 2026-10-06 08:00 | 2026-10-11 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1600 | Control Box | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-06 08:00 | 2026-10-11 16:00 | 5 | A1760 (FS +40h) | 464 | 2026-10-06 08:00 | 2026-10-11 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1610 | Design Feeding Parts | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-10-06 08:00 | 2026-10-07 16:00 | 2 | A1760 (FS +40h) | 8 | 2026-10-06 08:00 | 2026-10-07 16:00 | 2026-10-07 08:00 | 2026-10-08 16:00
A1790 | Fasteners Selection | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | Not Started | 0 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2 |  | 80 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2026-10-08 08:00 | 2026-10-09 16:00
A1900 | BASE | DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | In Progress | 0 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2 |  | 128 | 2026-09-27 08:00 | 2026-09-28 16:00 | 2026-10-15 08:00 | 2026-10-16 16:00
A1650 | Assembly of Feeding | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-10-06 08:00 | 2026-10-08 16:00 | 3 | A1610 (SS), A1610 (FF) | 8 | 2026-10-06 08:00 | 2026-10-08 16:00 | 2026-10-07 08:00 | 2026-10-09 16:00
A1660 | Assembly of Magazine | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-10-06 08:00 | 2026-10-08 16:00 | 3 | A1200 (SS), A1200 (FF) | 8 | 2026-10-06 08:00 | 2026-10-08 16:00 | 2026-10-07 08:00 | 2026-10-09 16:00
A1670 | Assembly Feeding with Magazine | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-10-09 08:00 | 2026-10-14 16:00 | 5 | A1650 (FS), A1660 (FS) | 8 | 2026-10-09 08:00 | 2026-10-14 16:00 | 2026-10-11 08:00 | 2026-10-15 16:00
A1680 | Assembly 3-DOF | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | In Progress | 0 | 2026-10-04 08:00 | 2026-10-08 16:00 | 5 | A1760 (FS +24h) | 48 | 2026-10-04 08:00 | 2026-10-08 16:00 | 2026-10-11 08:00 | 2026-10-15 16:00
A1690 | Assembly Electrical Box | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-10-07 08:00 | 2026-10-12 16:00 | 5 | A1180 (FS) | 24 | 2026-10-07 08:00 | 2026-10-12 16:00 | 2026-10-11 08:00 | 2026-10-15 16:00
A1700 | Assembly Consideration | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-10-09 08:00 | 2026-10-14 16:00 | 5 | A1790 (FS), A1690 (SS), A1690 (FF), A1680 (SS), A1670 (SS), A1680 (FF), A1670 (FF) | 8 | 2026-10-09 08:00 | 2026-10-14 16:00 | 2026-10-11 08:00 | 2026-10-15 16:00
A1710 | Assembly Fixation | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-09-28 08:00 | 2026-10-02 16:00 | 5 | A1790 (SS +8h), A1790 (FF +8h) | 96 | 2026-09-28 08:00 | 2026-10-02 16:00 | 2026-10-12 08:00 | 2026-10-16 16:00
A1800 | Whole Assembly | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-10-11 08:00 | 2026-10-27 16:00 | 15 | A1710 (SS), A1700 (SS +8h), A1710 (FF), A1700 (FF +8h) | 8 | 2026-10-11 08:00 | 2026-10-27 16:00 | 2026-10-12 08:00 | 2026-10-28 16:00
A1830 | Wire and harness | DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | Not Started | 0 | 2026-10-28 08:00 | 2026-10-30 16:00 | 3 | A1800 (SS +24h), A1800 (FF +24h) | 120 | 2026-10-28 08:00 | 2026-10-30 16:00 | 2026-11-26 08:00 | 2026-11-29 16:00
A1290 | StateFlow | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | On Hold | 0 | 2026-10-16 08:00 | 2026-10-21 16:00 | 5 | A1800 (SS +40h) | 48 | 2026-10-16 08:00 | 2026-10-21 16:00 | 2026-10-23 08:00 | 2026-10-28 16:00
A1300 | Define Pins | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | Not Started | 0 | 2026-10-22 08:00 | 2026-10-22 16:00 | 1 | A1290 (FS) | 48 | 2026-10-22 08:00 | 2026-10-22 16:00 | 2026-10-29 08:00 | 2026-10-29 16:00
A1310 | PID Code | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | Not Started | 0 | 2026-10-23 08:00 | 2026-10-28 16:00 | 5 | A1300 (FS) | 48 | 2026-10-23 08:00 | 2026-10-28 16:00 | 2026-10-30 08:00 | 2026-11-04 16:00
A1370 | 3-DOF Robotics | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | Not Started | 0 | 2026-10-29 08:00 | 2026-11-03 16:00 | 5 | A1310 (FS) | 304 | 2026-10-29 08:00 | 2026-11-03 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1380 | Sensors Calibration | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | Not Started | 0 | 2026-10-23 08:00 | 2026-10-28 16:00 | 5 | A1300 (FS) | 344 | 2026-10-23 08:00 | 2026-10-28 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1770 | HMI | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | Not Started | 0 | 2026-11-27 08:00 | 2026-12-02 16:00 | 5 | A1300 (FS +160h) | 184 | 2026-11-27 08:00 | 2026-12-02 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1780 | Communication Protocol | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | Not Started | 0 | 2026-11-27 08:00 | 2026-12-02 16:00 | 5 | A1300 (FS +160h) | 184 | 2026-11-27 08:00 | 2026-12-02 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1850 | Integration Code | DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | Not Started | 0 | 2026-11-27 08:00 | 2026-12-02 16:00 | 5 | A1310 (SS +160h), A1310 (FF +160h) | 48 | 2026-11-27 08:00 | 2026-12-02 16:00 | 2026-12-04 08:00 | 2026-12-09 16:00
A1220 | Wire Sizing | DESIGN1.5.2 | Tinker Line > Electrical & Control System > Wiring and Schematic | Not Started | 0 | 2026-10-28 08:00 | 2026-11-02 16:00 | 5 | A1300 (SS +40h) | 232 | 2026-10-28 08:00 | 2026-11-02 16:00 | 2026-12-13 08:00 | 2026-12-17 16:00
A1230 | Protues Simulation | DESIGN1.5.2 | Tinker Line > Electrical & Control System > Wiring and Schematic | Not Started | 0 | 2026-11-27 08:00 | 2026-12-02 16:00 | 5 | A1850 (SS) | 48 | 2026-11-27 08:00 | 2026-12-02 16:00 | 2026-12-04 08:00 | 2026-12-09 16:00
A1240 | Define Connectors | DESIGN1.5.2 | Tinker Line > Electrical & Control System > Wiring and Schematic | Not Started | 0 | 2026-10-28 08:00 | 2026-11-02 16:00 | 5 | A1830 (SS), A1830 (FF) | 312 | 2026-10-28 08:00 | 2026-11-02 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1250 | PCB Design | DESIGN1.5.2 | Tinker Line > Electrical & Control System > Wiring and Schematic | Not Started | 0 | 2026-11-27 08:00 | 2026-12-02 16:00 | 5 | A1230 (SS) | 48 | 2026-11-27 08:00 | 2026-12-02 16:00 | 2026-12-04 08:00 | 2026-12-09 16:00
A1260 | DC motor Model | DESIGN1.5.3 | Tinker Line > Electrical & Control System > Simulation | Not Started | 0 | 2026-10-28 08:00 | 2026-11-02 16:00 | 5 | A1800 (FS) | 96 | 2026-10-28 08:00 | 2026-11-02 16:00 | 2026-11-23 08:00 | 2026-11-27 16:00
A1270 | PID Model | DESIGN1.5.3 | Tinker Line > Electrical & Control System > Simulation | Not Started | 0 | 2026-10-28 08:00 | 2026-11-02 16:00 | 5 | A1260 (SS), A1260 (FF) | 96 | 2026-10-28 08:00 | 2026-11-02 16:00 | 2026-11-23 08:00 | 2026-11-27 16:00
A1280 | Circuit Simulation | DESIGN1.5.3 | Tinker Line > Electrical & Control System > Simulation | Not Started | 0 | 2026-10-28 08:00 | 2026-11-02 16:00 | 5 | A1270 (SS) | 96 | 2026-10-28 08:00 | 2026-11-02 16:00 | 2026-11-23 08:00 | 2026-11-27 16:00
A1640 | Multibody Simulation | DESIGN1.5.3 | Tinker Line > Electrical & Control System > Simulation | Not Started | 0 | 2026-09-27 08:00 | 2026-10-01 16:00 | 5 |  | 528 | 2026-09-27 08:00 | 2026-10-01 16:00 | 2026-12-24 08:00 | 2026-12-29 16:00
A1320 | Aluminum Extrusion | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-10-16 08:00 | 2026-10-18 16:00 | 2 | A1800 (SS +40h) | 416 | 2026-10-16 08:00 | 2026-10-18 16:00 | 2026-12-28 08:00 | 2026-12-29 16:00
A1330 | Actuators | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-10-16 08:00 | 2026-10-18 16:00 | 2 | A1800 (SS +40h) | 240 | 2026-10-16 08:00 | 2026-10-18 16:00 | 2026-12-02 08:00 | 2026-12-03 16:00
A1410 | Wires | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-11-24 08:00 | 2026-11-25 16:00 | 2 | A1220 (SS +80h), A1220 (FF +80h) | 232 | 2026-11-24 08:00 | 2026-11-25 16:00 | 2026-12-28 08:00 | 2026-12-29 16:00
A1420 | PCB | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-12-07 08:00 | 2026-12-08 16:00 | 2 | A1250 (FS +24h) | 48 | 2026-12-07 08:00 | 2026-12-08 16:00 | 2026-12-14 08:00 | 2026-12-15 16:00
A1450 | Conveyor Belts and Pullies | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-10-07 08:00 | 2026-10-08 16:00 | 2 | A1680 (SS), A1680 (FF) | 480 | 2026-10-07 08:00 | 2026-10-08 16:00 | 2026-12-28 08:00 | 2026-12-29 16:00
A1460 | Bolts and Nuts | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-10-14 08:00 | 2026-10-15 16:00 | 2 | A1790 (SS +120h), A1790 (FF +120h) | 184 | 2026-10-14 08:00 | 2026-10-15 16:00 | 2026-11-22 08:00 | 2026-11-23 16:00
A1470 | Electrical Components | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-11-06 08:00 | 2026-11-08 16:00 | 2 | A1280 (SS +40h), A1280 (FF +40h) | 96 | 2026-11-06 08:00 | 2026-11-08 16:00 | 2026-12-02 08:00 | 2026-12-03 16:00
A1740 | Wood | DESIGN1.6 | Tinker Line > Procurement | Not Started | 0 | 2026-10-15 08:00 | 2026-10-18 16:00 | 3 | A1670 (FS) | 112 | 2026-10-15 08:00 | 2026-10-18 16:00 | 2026-11-01 08:00 | 2026-11-03 16:00
A1390 | Magazine Parts | DESIGN1.7 | Tinker Line > Manufacturing | Not Started | 0 | 2026-11-02 08:00 | 2026-11-03 16:00 | 2 | A1670 (FS +120h), A1740 (FS +8h) | 152 | 2026-11-02 08:00 | 2026-11-03 16:00 | 2026-12-06 08:00 | 2026-12-07 16:00
A1750 | Feeding Parts | DESIGN1.7 | Tinker Line > Manufacturing | Not Started | 0 | 2026-11-02 08:00 | 2026-11-03 16:00 | 2 | A1670 (FS +120h), A1740 (FS +8h) | 152 | 2026-11-02 08:00 | 2026-11-03 16:00 | 2026-12-06 08:00 | 2026-12-07 16:00
A1860 | LID Manufacturing | DESIGN1.7 | Tinker Line > Manufacturing | Not Started | 0 | 2026-10-20 08:00 | 2026-10-21 16:00 | 2 | A1160 (FS +120h), A1740 (FS +8h) | 144 | 2026-10-20 08:00 | 2026-10-21 16:00 | 2026-11-22 08:00 | 2026-11-23 16:00
A1870 | Base Manufacturing | DESIGN1.7 | Tinker Line > Manufacturing | Not Started | 0 | 2026-10-25 08:00 | 2026-10-26 16:00 | 2 | A1170 (FS +120h), A1740 (FS +8h) | 112 | 2026-10-25 08:00 | 2026-10-26 16:00 | 2026-11-22 08:00 | 2026-11-23 16:00
A1880 | Electrical Box | DESIGN1.7 | Tinker Line > Manufacturing | Not Started | 0 | 2026-11-05 08:00 | 2026-11-06 16:00 | 2 | A1690 (FS +160h), A1740 (FS +8h) | 32 | 2026-11-05 08:00 | 2026-11-06 16:00 | 2026-11-22 08:00 | 2026-11-23 16:00
A1890 | BASE Manufacturing | DESIGN1.7 | Tinker Line > Manufacturing | Not Started | 0 | 2026-10-25 08:00 | 2026-10-26 16:00 | 2 | A1900 (FS +160h), A1740 (FS +40h) | 112 | 2026-10-25 08:00 | 2026-10-26 16:00 | 2026-11-22 08:00 | 2026-11-23 16:00
A1430 | Real Mechanical Assembly | DESIGN1.8 | Tinker Line > Assembly & Integration | Not Started | 0 | 2026-11-23 08:00 | 2026-12-15 16:00 | 20 | A1800 (FS +96h), A1800 (FF +96h), A1880 (FS), A1870 (FS), A1870 (FF), A1860 (FS), A1890 (FS), A1460 (FS) | 8 | 2026-11-23 08:00 | 2026-12-15 16:00 | 2026-11-24 08:00 | 2026-12-16 16:00
A1440 | Hardware Wiring | DESIGN1.8 | Tinker Line > Assembly & Integration | Not Started | 0 | 2026-12-07 08:00 | 2026-12-17 16:00 | 10 | A1830 (SS +80h), A1830 (FF +80h), A1430 (SS +16h), A1430 (FF +16h) | 8 | 2026-12-07 08:00 | 2026-12-17 16:00 | 2026-12-08 08:00 | 2026-12-18 16:00
A1480 | Test DC-Motors | DESIGN1.10.1 | Tinker Line > Testing & Commissioning > Test Component | Not Started | 0 | 2026-10-19 08:00 | 2026-10-21 16:00 | 3 | A1330 (FS) | 240 | 2026-10-19 08:00 | 2026-10-21 16:00 | 2026-12-04 08:00 | 2026-12-07 16:00
A1490 | Sensors | DESIGN1.10.1 | Tinker Line > Testing & Commissioning > Test Component | Not Started | 0 | 2026-11-15 08:00 | 2026-11-23 16:00 | 3 | A1470 (FS) | 96 | 2026-11-15 08:00 | 2026-11-23 16:00 | 2026-12-04 08:00 | 2026-12-07 16:00
A1500 | Servo Motor | DESIGN1.10.1 | Tinker Line > Testing & Commissioning > Test Component | Not Started | 0 | 2026-10-19 08:00 | 2026-10-21 16:00 | 3 | A1330 (FS) | 240 | 2026-10-19 08:00 | 2026-10-21 16:00 | 2026-12-04 08:00 | 2026-12-07 16:00
A1510 | Magnetic Part | DESIGN1.10.1 | Tinker Line > Testing & Commissioning > Test Component | Not Started | 0 | 2026-11-15 08:00 | 2026-11-23 16:00 | 3 | A1470 (FS) | 96 | 2026-11-15 08:00 | 2026-11-23 16:00 | 2026-12-04 08:00 | 2026-12-07 16:00
A1840 | PCB Test | DESIGN1.10.1 | Tinker Line > Testing & Commissioning > Test Component | Not Started | 0 | 2026-12-09 08:00 | 2026-12-11 16:00 | 3 | A1420 (FS) | 48 | 2026-12-09 08:00 | 2026-12-11 16:00 | 2026-12-16 08:00 | 2026-12-18 16:00
A1520 | Test X-Axis Path | DESIGN1.10.2 | Tinker Line > Testing & Commissioning > Test System | Not Started | 0 | 2026-10-22 08:00 | 2026-10-27 16:00 | 5 | A1480 (FS) | 240 | 2026-10-22 08:00 | 2026-10-27 16:00 | 2026-12-08 08:00 | 2026-12-13 16:00
A1530 | Test Y-Axis Path | DESIGN1.10.2 | Tinker Line > Testing & Commissioning > Test System | Not Started | 0 | 2026-10-22 08:00 | 2026-10-27 16:00 | 5 | A1480 (FS) | 240 | 2026-10-22 08:00 | 2026-10-27 16:00 | 2026-12-08 08:00 | 2026-12-13 16:00
A1540 | Test Z-Axis Path | DESIGN1.10.2 | Tinker Line > Testing & Commissioning > Test System | Not Started | 0 | 2026-11-24 08:00 | 2026-11-29 16:00 | 5 | A1480 (FS), A1510 (FS), A1500 (FS) | 96 | 2026-11-24 08:00 | 2026-11-29 16:00 | 2026-12-08 08:00 | 2026-12-13 16:00
A1550 | Test Magazine | DESIGN1.10.2 | Tinker Line > Testing & Commissioning > Test System | Not Started | 0 | 2026-11-24 08:00 | 2026-11-29 16:00 | 5 | A1480 (FS), A1390 (FS), A1490 (FS) | 96 | 2026-11-24 08:00 | 2026-11-29 16:00 | 2026-12-08 08:00 | 2026-12-13 16:00
A1560 | Test Feeding | DESIGN1.10.2 | Tinker Line > Testing & Commissioning > Test System | Not Started | 0 | 2026-11-24 08:00 | 2026-11-29 16:00 | 5 | A1480 (FS), A1750 (FS), A1490 (FS) | 96 | 2026-11-24 08:00 | 2026-11-29 16:00 | 2026-12-08 08:00 | 2026-12-13 16:00
A1570 | Test 3-DOF Robot | DESIGN1.10.3 | Tinker Line > Testing & Commissioning > Test Module | Not Started | 0 | 2026-11-30 08:00 | 2026-12-04 16:00 | 5 | A1530 (FS), A1520 (FS), A1540 (FS) | 96 | 2026-11-30 08:00 | 2026-12-04 16:00 | 2026-12-14 08:00 | 2026-12-18 16:00
A1580 | Test Magazine with Feeding | DESIGN1.10.3 | Tinker Line > Testing & Commissioning > Test Module | Not Started | 0 | 2026-11-30 08:00 | 2026-12-04 16:00 | 5 | A1550 (FS), A1560 (FS) | 96 | 2026-11-30 08:00 | 2026-12-04 16:00 | 2026-12-14 08:00 | 2026-12-18 16:00
A1620 | Test Whole System | DESIGN1.10.4 | Tinker Line > Testing & Commissioning > Test Integration | Not Started | 0 | 2026-12-18 08:00 | 2026-12-25 16:00 | 7 | A1570 (FS), A1580 (FS), A1840 (FS), A1440 (FS) | 8 | 2026-12-18 08:00 | 2026-12-25 16:00 | 2026-12-20 08:00 | 2026-12-27 16:00
A1630 | Repair for the final submission | DESIGN1.11 | Tinker Line > Handover | Not Started | 0 | 2026-12-27 08:00 | 2026-12-28 16:00 | 2 | A1620 (FS) | 8 | 2026-12-27 08:00 | 2026-12-28 16:00 | 2026-12-28 08:00 | 2026-12-29 16:00

## Pivot Summary
`
KPI | Value |  | Status | Activities | Avg Progress
Total Activities | 82 |  | Not Started | 68 | 0%
Total Planned Duration (days) | 278 |  | In Progress | 4 | 0%
Completed Activities | 8 |  | Completed | 8 | 0%
In Progress Activities | 400% |  | On Hold | 2 | 0%
Not Started Activities | 68
On Hold Activities | 2
Average Progress | 0%
WBS / Work Package Summary
WBS Code | WBS | Activities | Duration (days) | Avg Progress
DESIGN1.1 | Tinker Line > MilesStones | 9 | 0 | 0%
DESIGN1.10.1 | Tinker Line > Testing & Commissioning > Test Component | 5 | 15 | 0%
DESIGN1.10.2 | Tinker Line > Testing & Commissioning > Test System | 5 | 25 | 0%
DESIGN1.10.3 | Tinker Line > Testing & Commissioning > Test Module | 2 | 10 | 0%
DESIGN1.10.4 | Tinker Line > Testing & Commissioning > Test Integration | 1 | 7 | 0%
DESIGN1.11 | Tinker Line > Handover | 1 | 2 | 0%
DESIGN1.2 | Tinker Line > Project Initiation | 3 | 6 | 0%
DESIGN1.3 | Tinker Line > Requirements & Planning | 3 | 3 | 0%
DESIGN1.4.1 | Tinker Line > Mechanical Design > Parts | 12 | 26 | 0%
DESIGN1.4.2 | Tinker Line > Mechanical Design > Assembly | 9 | 49 | 0%
DESIGN1.5.1 | Tinker Line > Electrical & Control System > Embedded Code | 8 | 36 | 0%
DESIGN1.5.2 | Tinker Line > Electrical & Control System > Wiring and Schematic | 4 | 20 | 0%
DESIGN1.5.3 | Tinker Line > Electrical & Control System > Simulation | 4 | 20 | 0%
DESIGN1.6 | Tinker Line > Procurement | 8 | 17 | 0%
DESIGN1.7 | Tinker Line > Manufacturing | 6 | 12 | 0%
DESIGN1.8 | Tinker Line > Assembly & Integration | 2 | 30 | 0%

## Interactive Gantt
DESIGN1 — INTERACTIVE PRIMAVERA GANTT CHART
Status Filter | All Statuses | WBS Filter | All WBS |  | Planned | Completed | Today | Project | 27-Sep-2026 → 28-Dec-2026
Activity ID | Activity Name | WBS Code | Start | Finish | Status | Progress | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28
A1000 | Project Initiation | DESIGN1.1 | 2026-09-27 08:00 | 2026-09-27 08:00 | Not Started | 0%
A1010 | Requirements & Planning | DESIGN1.1 | 2026-09-29 16:00 | 2026-09-29 16:00 | Not Started | 0%
A1030 | Mechanical Design | DESIGN1.1 | 2026-10-30 16:00 | 2026-10-30 16:00 | Not Started | 0%
A1040 | Electrical & Control System | DESIGN1.1 | 2026-12-02 16:00 | 2026-12-02 16:00 | Not Started | 0%
A1050 | Procurement | DESIGN1.1 | 2026-12-08 16:00 | 2026-12-08 16:00 | Not Started | 0%
A1060 | Manufacturing | DESIGN1.1 | 2026-10-30 16:00 | 2026-10-30 16:00 | Not Started | 0%
A1070 | Assembly & Integration | DESIGN1.1 | 2026-12-17 16:00 | 2026-12-17 16:00 | Not Started | 0%
A1090 | Testing & Commissioning | DESIGN1.1 | 2026-12-25 16:00 | 2026-12-25 16:00 | Not Started | 0%
A1100 | Handover | DESIGN1.1 | 2026-12-28 16:00 | 2026-12-28 16:00 | Not Started | 0%
A1110 | Define Project Objectives | DESIGN1.2 | 2026-09-27 08:00 | 2026-09-28 16:00 | Not Started | 0%
A1120 | Sketches | DESIGN1.2 | 2026-09-27 08:00 | 2026-09-28 16:00 | Not Started | 0%
A1130 | Settle to Idea | DESIGN1.2 | 2026-09-27 08:00 | 2026-09-28 16:00 | Not Started | 0%
A1140 | Set Initial Project Schedule | DESIGN1.3 | 2026-09-28 08:00 | 2026-09-28 16:00 | Not Started | 0%
A1150 | Estimate BOM | DESIGN1.3 | 2026-09-28 08:00 | 2026-09-28 16:00 | Not Started | 0%
A1760 | Assign Resources | DESIGN1.3 | 2026-09-29 08:00 | 2026-09-29 16:00 | Not Started | 0%
A1160 | LID | DESIGN1.4.1 | 2026-09-30 08:00 | 2026-09-30 16:00 | Not Started | 0%
A1170 | Base | DESIGN1.4.1 | 2026-10-06 08:00 | 2026-10-06 16:00 | Not Started | 0%
A1180 | Electrical Box | DESIGN1.4.1 | 2026-10-06 08:00 | 2026-10-06 16:00 | Not Started | 0%
A1190 | Magnetic End Effector | DESIGN1.4.1 | 2026-10-07 08:00 | 2026-10-08 16:00 | Not Started | 0%
A1200 | Design Magazine Parts | DESIGN1.4.1 | 2026-10-06 08:00 | 2026-10-07 16:00 | Not Started | 0%
A1210 | Shaft Analysis | DESIGN1.4.1 | 2026-10-11 08:00 | 2026-10-11 16:00 | Not Started | 0%
A1340 | Actuator Sizing | DESIGN1.4.1 | 2026-10-16 08:00 | 2026-10-18 16:00 | Not Started | 0%
A1590 | Storage | DESIGN1.4.1 | 2026-10-06 08:00 | 2026-10-11 16:00 | Not Started | 0%
A1600 | Control Box | DESIGN1.4.1 | 2026-10-06 08:00 | 2026-10-11 16:00 | Not Started | 0%
A1610 | Design Feeding Parts | DESIGN1.4.1 | 2026-10-06 08:00 | 2026-10-07 16:00 | Not Started | 0%
A1790 | Fasteners Selection | DESIGN1.4.1 | 2026-09-27 08:00 | 2026-09-28 16:00 | Not Started | 0%
A1900 | BASE | DESIGN1.4.1 | 2026-09-27 08:00 | 2026-09-28 16:00 | Not Started | 0%
A1650 | Assembly of Feeding | DESIGN1.4.2 | 2026-10-06 08:00 | 2026-10-08 16:00 | Not Started | 0%
A1660 | Assembly of Magazine | DESIGN1.4.2 | 2026-10-06 08:00 | 2026-10-08 16:00 | Not Started | 0%
A1670 | Assembly Feeding with Magazine | DESIGN1.4.2 | 2026-10-09 08:00 | 2026-10-14 16:00 | Not Started | 0%
A1680 | Assembly 3-DOF | DESIGN1.4.2 | 2026-10-04 08:00 | 2026-10-08 16:00 | Not Started | 0%
A1690 | Assembly Electrical Box | DESIGN1.4.2 | 2026-10-07 08:00 | 2026-10-12 16:00 | Not Started | 0%
A1700 | Assembly Consideration | DESIGN1.4.2 | 2026-10-09 08:00 | 2026-10-14 16:00 | Not Started | 0%
A1710 | Assembly Fixation | DESIGN1.4.2 | 2026-09-28 08:00 | 2026-10-02 16:00 | Not Started | 0%
A1800 | Whole Assembly | DESIGN1.4.2 | 2026-10-11 08:00 | 2026-10-27 16:00 | Not Started | 0%
A1830 | Wire and harness | DESIGN1.4.2 | 2026-10-28 08:00 | 2026-10-30 16:00 | Not Started | 0%
A1290 | StateFlow | DESIGN1.5.1 | 2026-10-16 08:00 | 2026-10-21 16:00 | Not Started | 0%
A1300 | Define Pins | DESIGN1.5.1 | 2026-10-22 08:00 | 2026-10-22 16:00 | Not Started | 0%
A1310 | PID Code | DESIGN1.5.1 | 2026-10-23 08:00 | 2026-10-28 16:00 | Not Started | 0%
A1370 | 3-DOF Robotics | DESIGN1.5.1 | 2026-10-29 08:00 | 2026-11-03 16:00 | Not Started | 0%
A1380 | Sensors Calibration | DESIGN1.5.1 | 2026-10-23 08:00 | 2026-10-28 16:00 | Not Started | 0%
A1770 | HMI | DESIGN1.5.1 | 2026-11-27 08:00 | 2026-12-02 16:00 | Not Started | 0%
A1780 | Communication Protocol | DESIGN1.5.1 | 2026-11-27 08:00 | 2026-12-02 16:00 | Not Started | 0%
A1850 | Integration Code | DESIGN1.5.1 | 2026-11-27 08:00 | 2026-12-02 16:00 | Not Started | 0%
A1220 | Wire Sizing | DESIGN1.5.2 | 2026-10-28 08:00 | 2026-11-02 16:00 | Not Started | 0%
A1230 | Protues Simulation | DESIGN1.5.2 | 2026-11-27 08:00 | 2026-12-02 16:00 | Not Started | 0%
A1240 | Define Connectors | DESIGN1.5.2 | 2026-10-28 08:00 | 2026-11-02 16:00 | Not Started | 0%
A1250 | PCB Design | DESIGN1.5.2 | 2026-11-27 08:00 | 2026-12-02 16:00 | Not Started | 0%
A1260 | DC motor Model | DESIGN1.5.3 | 2026-10-28 08:00 | 2026-11-02 16:00 | Not Started | 0%
A1270 | PID Model | DESIGN1.5.3 | 2026-10-28 08:00 | 2026-11-02 16:00 | Not Started | 0%
A1280 | Circuit Simulation | DESIGN1.5.3 | 2026-10-28 08:00 | 2026-11-02 16:00 | Not Started | 0%
A1640 | Multibody Simulation | DESIGN1.5.3 | 2026-09-27 08:00 | 2026-10-01 16:00 | Not Started | 0%
A1320 | Aluminum Extrusion | DESIGN1.6 | 2026-10-16 08:00 | 2026-10-18 16:00 | Not Started | 0%
A1330 | Actuators | DESIGN1.6 | 2026-10-16 08:00 | 2026-10-18 16:00 | Not Started | 0%
A1410 | Wires | DESIGN1.6 | 2026-11-24 08:00 | 2026-11-25 16:00 | Not Started | 0%
A1420 | PCB | DESIGN1.6 | 2026-12-07 08:00 | 2026-12-08 16:00 | Not Started | 0%
A1450 | Conveyor Belts and Pullies | DESIGN1.6 | 2026-10-07 08:00 | 2026-10-08 16:00 | Not Started | 0%
A1460 | Bolts and Nuts | DESIGN1.6 | 2026-10-14 08:00 | 2026-10-15 16:00 | Not Started | 0%
A1470 | Electrical Components | DESIGN1.6 | 2026-11-06 08:00 | 2026-11-08 16:00 | Not Started | 0%
A1740 | Wood | DESIGN1.6 | 2026-10-15 08:00 | 2026-10-18 16:00 | Not Started | 0%
A1390 | Magazine Parts | DESIGN1.7 | 2026-11-02 08:00 | 2026-11-03 16:00 | Not Started | 0%
A1750 | Feeding Parts | DESIGN1.7 | 2026-11-02 08:00 | 2026-11-03 16:00 | Not Started | 0%
A1860 | LID Manufacturing | DESIGN1.7 | 2026-10-20 08:00 | 2026-10-21 16:00 | Not Started | 0%
A1870 | Base Manufacturing | DESIGN1.7 | 2026-10-25 08:00 | 2026-10-26 16:00 | Not Started | 0%
A1880 | Electrical Box | DESIGN1.7 | 2026-11-05 08:00 | 2026-11-06 16:00 | Not Started | 0%
A1890 | BASE Manufacturing | DESIGN1.7 | 2026-10-25 08:00 | 2026-10-26 16:00 | Not Started | 0%
A1430 | Real Mechanical Assembly | DESIGN1.8 | 2026-11-23 08:00 | 2026-12-15 16:00 | Not Started | 0%
A1440 | Hardware Wiring | DESIGN1.8 | 2026-12-07 08:00 | 2026-12-17 16:00 | Not Started | 0%
A1480 | Test DC-Motors | DESIGN1.10.1 | 2026-10-19 08:00 | 2026-10-21 16:00 | Not Started | 0%
A1490 | Sensors | DESIGN1.10.1 | 2026-11-15 08:00 | 2026-11-23 16:00 | Not Started | 0%
A1500 | Servo Motor | DESIGN1.10.1 | 2026-10-19 08:00 | 2026-10-21 16:00 | Not Started | 0%
A1510 | Magnetic Part | DESIGN1.10.1 | 2026-11-15 08:00 | 2026-11-23 16:00 | Not Started | 0%
A1840 | PCB Test | DESIGN1.10.1 | 2026-12-09 08:00 | 2026-12-11 16:00 | Not Started | 0%
A1520 | Test X-Axis Path | DESIGN1.10.2 | 2026-10-22 08:00 | 2026-10-27 16:00 | Not Started | 0%
A1530 | Test Y-Axis Path | DESIGN1.10.2 | 2026-10-22 08:00 | 2026-10-27 16:00 | Not Started | 0%
A1540 | Test Z-Axis Path | DESIGN1.10.2 | 2026-11-24 08:00 | 2026-11-29 16:00 | Not Started | 0%
A1550 | Test Magazine | DESIGN1.10.2 | 2026-11-24 08:00 | 2026-11-29 16:00 | Not Started | 0%
A1560 | Test Feeding | DESIGN1.10.2 | 2026-11-24 08:00 | 2026-11-29 16:00 | Not Started | 0%
A1570 | Test 3-DOF Robot | DESIGN1.10.3 | 2026-11-30 08:00 | 2026-12-04 16:00 | Not Started | 0%
A1580 | Test Magazine with Feeding | DESIGN1.10.3 | 2026-11-30 08:00 | 2026-12-04 16:00 | Not Started | 0%
A1620 | Test Whole System | DESIGN1.10.4 | 2026-12-18 08:00 | 2026-12-25 16:00 | Not Started | 0%
A1630 | Repair for the final submission | DESIGN1.11 | 2026-12-27 08:00 | 2026-12-28 16:00 | Not Started | 0%

## _Lists (hidden)
All WBS
DESIGN1.1
DESIGN1.10.1
DESIGN1.10.2
DESIGN1.10.3
DESIGN1.10.4
DESIGN1.11
DESIGN1.2
DESIGN1.3
DESIGN1.4.1
DESIGN1.4.2
DESIGN1.5.1
DESIGN1.5.2
DESIGN1.5.3
DESIGN1.6
DESIGN1.7
DESIGN1.8

## WBS Structure
DESIGN1 — PRIMAVERA WBS STRUCTURE
WBS ID | Parent WBS ID | WBS Code | WBS Name | Parent Name | Sequence
26010 | 3063 | DESIGN1 | Tinker Line |  | 7
26012 | 26010 | DESIGN1.1 | MilesStones | Tinker Line | 1
26014 | 26010 | DESIGN1.2 | Project Initiation | Tinker Line | 2
26015 | 26010 | DESIGN1.3 | Requirements & Planning | Tinker Line | 3
26016 | 26010 | DESIGN1.4 | Mechanical Design | Tinker Line | 4
26017 | 26010 | DESIGN1.5 | Electrical & Control System | Tinker Line | 6
26018 | 26010 | DESIGN1.6 | Procurement | Tinker Line | 7
26019 | 26010 | DESIGN1.7 | Manufacturing | Tinker Line | 8
26020 | 26010 | DESIGN1.8 | Assembly & Integration | Tinker Line | 9
26022 | 26010 | DESIGN1.10 | Testing & Commissioning | Tinker Line | 11
26023 | 26010 | DESIGN1.11 | Handover | Tinker Line | 13
26024 | 26017 | DESIGN1.5.1 | Embedded Code | Electrical & Control System | 1
26025 | 26017 | DESIGN1.5.2 | Wiring and Schematic | Electrical & Control System | 2
26026 | 26017 | DESIGN1.5.3 | Simulation | Electrical & Control System | 3
26027 | 26016 | DESIGN1.4.1 | Parts | Mechanical Design | 1
26028 | 26016 | DESIGN1.4.2 | Assembly | Mechanical Design | 3
26030 | 26022 | DESIGN1.10.1 | Test Component | Testing & Commissioning | 1
26031 | 26022 | DESIGN1.10.2 | Test System | Testing & Commissioning | 2
26032 | 26022 | DESIGN1.10.3 | Test Module | Testing & Commissioning | 3
26033 | 26022 | DESIGN1.10.4 | Test Integration | Testing & Commissioning | 4